## WP with COA
Activity |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Certificate of Authority
1 | Acquisition of Endorsement and Provisional Permits | bar: Year 1 Q1 to Year 2 Q2
2 | Table-top assessment and review | bar: Year 1 Q1
3 | Reconnaissance Geology and Geochemistry Surveys | bar: Year 1 Q2
4 | 2G Surveys and Assessments | bar: Year 1 Q3 to Year 1 Q4
5 | Geophysical Surveys and Assessments | bar: Year 2 Q1 to Year 2 Q2
6 | Remote Sensing Surveys (i.e. LiDAR) | bar: Year 2 Q3 to Year 2 Q4
7 | Initial Pre-Feasibility Study | bar: Year 3 Q1
8 | Infill and Refinement Surveys | bar: Year 3 Q2 to Year 3 Q3
9 | Identification and Acquisition of Permits for drilling preparations | bar: Year 3 Q2 to Year 3 Q4
10 | Final Pre-Feasibility Studies and Preliminary Drilling Targets | bar: Year 3 Q4
|  |  | Year 1 Q1: Year 1; Year 2 Q1: Year 2; Year 3 Q1: Year 3 | Year 4 |  |  |  | Year 5
| GSC Pre-Development Term |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Complete GSC Application and acquisition of necessary permits and endorsements | bar: Year 1 Q1 to Year 1 Q3
2 | Exploration Drilling
Drilling civil works and procurement of long lead items | bar: Year 1 Q2 to Year 2 Q1
Exploration well drilling and testing | bar: Year 2 Q2 to Year 2 Q3
Update of Resource Assessment | bar: Year 2 Q4
3 | Appraisal Drilling
Drilling civil works and procurement of long lead items | bar: Year 3 Q1 to Year 3 Q2
Appraisal well drilling and testing | bar: Year 3 Q3 to Year 4 Q1
Update of Resource Assessment | bar: Year 4 Q2
4 | Enviromental Impact Assessment | bar: Year 4 Q1 to Year 5 Q3
5 | Other Permits and Clearances | bar: Year 4 Q1 to Year 5 Q3
6 | Off-take/Market Negotiations | bar: Year 4 Q1 to Year 5 Q3
7 | System/Grid Impact Study | bar: Year 4 Q1 to Year 5 Q3
8 | Secure Financing | bar: Year 4 Q3 to Year 5 Q3
9 | Feasibility Study | bar: Year 5 Q2 to Year 5 Q3
10 | Tender for EPC Contracts | bar: Year 5 Q2 to Year 5 Q3
11 | Declaration of Commerciality | bar: Year 5 Q4

## WP without COA
Activity |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
GSC Pre-Development Term
1 | Acquisition of Endorsement and Permits | bar: Year 1 Q1 to Year 3 Q4
2 | Table-top assessment and review | bar: Year 1 Q1
3 | 2G Surveys and Assessments | bar: Year 1 Q2
4 | Geophysical Surveys and Assessments | bar: Year 1 Q3 to Year 1 Q4
5 | Remote Sensing Surveys (i.e. LiDAR) | bar: Year 1 Q4
6 | Pre-Feasibility Studies and Preliminary Drilling Targets | bar: Year 2 Q1
7 | Exploration Drilling
Drilling civil works and procurement of long lead items | bar: Year 2 Q2 to Year 2 Q3
Exploration well drilling and testing | bar: Year 2 Q4
Update of Resource Assessment | bar: Year 2 Q4
8 | Appraisal Drilling
Drilling civil works and procurement of long lead items | bar: Year 3 Q1
Appraisal well drilling and testing | bar: Year 3 Q2 to Year 3 Q3
Update of Resource Assessment | bar: Year 3 Q3
9 | Enviromental Impact Assessment | bar: Year 3 Q4 to Year 5 Q3
10 | System/Grid Impact Study | bar: Year 3 Q4 to Year 5 Q3
11 | Off-take/Market Negotiations | bar: Year 4 Q1 to Year 5 Q3
12 | Secure Financing | bar: Year 4 Q3 to Year 5 Q3
13 | Feasibility Study | bar: Year 5 Q2 to Year 5 Q3
14 | Tender for EPC Contracts | bar: Year 5 Q2 to Year 5 Q3
15 | Declaration of Commerciality | bar: Year 5 Q4